## Sheet1
Week # | To Do | Owned by | Deadline | Status | Comments
Week 10 (26 August - 1 September) | Set up Implementation Plan for everyone | Emily Teodoro | 2019-01-09
| Write up spreadsheet for plan of implementation | Emily Teodoro | 2019-01-09
Week 10 (2 September - 8 September) | Update Paper Protoype | Felix Andrei Perdo IV and Emily Teodoro | 2019-04-09
| Draw/Write Paper Protoype | Felix Andrei Perdo IV | 2019-04-09
| Test Paper Protoype | Felix Andrei Pedro IV and Emily Teodoro | 2019-06-09 |  | The group tested the paper prototype to see if there is in need of improvements or simplification for the UI
| Update Paper Protoype | Emily Teodoro | 2019-07-09 |  | The group made the simplified the UI and decided the name of the app to be COOP
Week 11 (9 September - 15 September) | Test Paper Prototype | Emily Teodoro and Felix Andrei Pedro IV | 2019-09-09 |  | The group asked people to test out the Final Paper Protoype (The same two people that tested the first one which are Jep Ramos and Kean Coria)
| Film Paper Prototype | Emily Teodoro and Michael Menez | 2019-10-09 |  | The group took a video of the testing.
| Make Wireframe powerpoint | Emily Teodoro, Felix Andrei Pedro IV, and Michael Menez | 2019-11-09
| Make Mock Up powerpoint | Emily Teodoro and Michael Menez | 2019-11-09
| Making of app in Ionic | Michael Menez | 15/9/2019
| Testing of app in Ionic | Emily Teodoro, Felix Andrei Pedro IV, and Michael Menez | 17/9/2019